CONTRACT FOR BUILDING WORK

Constructive choice Ltd, Registered With Company house #10348438

Unit 1 Trentview court, Nottingham, NG2 3FX

FORM OF AGREEMENT

DATE: #todays date#

PARTIES:

(Client) #client name#

#client address#

(the "Contractor") Constructive Choice Ltd represented by Sergej Safoncik, 271b Ilkeston road, Stapleford, Nottingham, England, NG9 8JD

INTRODUCTION

The Client has #type of work# project at #project address#

and wishes to appoint the Contractor to carry out certain work (the Works) in accordance with this Form of Agreement and the attached Terms and Conditions.

THE PARTIES AGREE as follows:

1.	The Works will commence on #project start date#, the Effective Date.

2.	The Works are due for completion on #project end date#, the Completion Date.

3.	Details of the Works and other requirements are set out in the attached Schedule 1.

4.	The Contract Price for #type of work# is £ #total amount including profit and vat# for labour and materials. A detailed breakdown of this amount is shown in the attached quote and schedule’s sheet and works specifications document along with the materials provisions. This is fixed price for the works specified in Schedule 2. It can be changed if both parties agrees or if there will be any unforeseen works found or any circumstances which are beyond contractor’s or client’s control.

5.	Special terms, if any, are set out in Schedule 3

6.	The Contract between the Client and the Contractor consists of this Form of Agreement, the attached Terms & Conditions, Appendix and Schedules and comes into effect upon signature.

SIGNED by:

for and on behalf of the Contractor

SIGNED by:

the Client

TERMS & CONDITIONS

FOR

BUILDING WORK

1.	CONTRACTOR OBLIGATIONS

1.1	The Contractor shall carry out and complete the Works in accordance with the Contract so that the Works are completed no later than the Completion Date.

1.2	All Works including all materials and equipment supplied by the Contractor shall conform to the requirements of the Contract and shall be of good quality and suitable for the purposes for which they are intended. Notes on who provides materials will be in the specification, schedule 1.

1.3	The Works shall be performed in an efficient and timely manner to the reasonable satisfaction of the Client and shall keep people on site.

1.4	To the extent that the Contractor is responsible for design the Contractor shall exercise reasonable skill and care to an appropriate professional standard to the plans attached.

1.5	The Contractor shall only employ personnel who are appropriately experienced and skilled in their particular fields whom they have used before and are satisfied they are of a good standard.

1.6	The Contractor shall comply with reasonable instructions of the Client, subject to a right of reasonable objection.

2.	CLIENT OBLIGATIONS

2.1	The Client shall give the Contractor access to the Site during the agreed working hours, and the first date for access is shown in the Appendix.

2.2	The Client shall respond as soon as reasonably practicable to all requests from the Contractor for information, approvals or decisions so as not to delay the Project.

2.3	The Client shall have access to the Works during the Contract and must observe all site safety regulations.

3.	PLANNING, PERMITS & CDM

3.1	Unless otherwise shown in the Appendix, the Contractor will be responsible (either directly or through their architect) for obtaining planning consent for the Works and building regulations approvals and any party wall consents, while the Client will be responsible to cover these expenses. Each of the parties shall comply with planning and building regulations insofar as these are relevant to each of them. i.e. the work should meet the relevant regulations for it to be deemed complete.

3.3	Any delay in obtaining licences and permits for which the Contractor is responsible shall be at the risk of the Contractor except to the extent the delay is unforeseeable.

3.4	Where the CDM Regulations apply:

(a)	the Client agrees to appoint the Contractor as the principal contractor (unless another principal contractor is named in the Appendix);

(b)	each of the Client and Contractor shall comply with their respective obligations under those Regulations.

4.	REPRESENTATIVES

4.1	The Client may appoint a third party as their representative to liaise with the Contractor and give instructions and approvals of a day-to-day nature arising under the Contract.  However, no extra cost, time extension or material change in the scope of work can be authorised by the Client’s representative without the prior written consent of the Client.

4.2	When the Works are being performed on the Site, the Contractor shall nominate a Contractor's representative whose appointment shall be subject to the Client's prior approval.  The Contractor's representative shall be based at the Site as required during the Contract and authorised to represent the Contractor in all matters relating to the Contract.

5.	WORK AT SITE

5.1	The Contractor shall comply with the Client's reasonable directions with respect to activities on Site and shall not interfere with any activities of the Client or of any third party engaged by the Client.  When the Contractor is one of a number of contractors appointed by the Client, the Contractor must co-ordinate their work with the other contractors so as to avoid disruption or delay to the overall Project programme.

5.2	Normal working hours are 9.00 am to 5.00 pm on weekdays (excluding public holidays) unless otherwise shown in the Appendix.

5.3	Any utility services (water & electricity) to be provided free of charge by the Client are identified in the Appendix.

5.4	The Contractor must ensure that their employees and sub-contractors comply with all health and safety regulations.  Safety equipment shall be worn whenever required.

5.5	The Contractor shall be at the Site regularly during the agreed working hours, store equipment at the end of each working day and leave the Site in a clean and tidy condition and secure the site to ensure materials are kept safe.

5.6	Any damage caused to the Client’s property or contents or any neighbouring property must be made good at the Contractor’s expense.

5.7	The Contractor shall ensure that on Completion all services and equipment have been tested satisfactorily, the newly constructed work is ready for occupation and the Site is left secure and in a clean condition fit for other works to be completed (painting/flooring).

5.8	If at any time, in the Client’s reasonable opinion, the presence of anyone working at the Site is unacceptable, the Contractor must replace that person upon request.

6.	PRICE AND PAYMENT

6.1	The Contractor acknowledges that it has inspected the Site and is satisfied that the Contract Price is sufficient for the risks, difficulties and costs of completing the Works that are reasonably foreseeable by a competent contractor, including (but not limited to) design, access, ground works, construction, fitting out and completion to the satisfaction of the Client.

6.2	The Contract Price shall be payable by instalments as shown in Schedule 2.  The Contractor shall submit a payment application (i.e. invoice) to the Client for each instalment that is due with relevant supporting data and each application shall be paid within the Friday following the payment application (i.e. invoice) after works have been checked by the client and signed off. If the client is away then pictures or videos of completed works will be sent before payment.

6.3	If the Client has reasons for paying less than the full amount of any payment application, the Client shall, not less than three days before the date for payment of that amount, give notice to the Contractor specifying the amount the Client considers to be due, each amount to be withheld and the reasons.  If the Contractor is dissatisfied with the notice, the matter shall be resolved in accordance with Clause 16.  Any disputed item that is subsequently approved for payment shall be included in the Contractor's application for the month in which the dispute is resolved.

6.4	Payment does not imply that the Works have been performed in accordance with the Contract.

6.5	The Client shall have the right to examine (or engage a qualified professional consultant to examine) the Contractor's records for the purposes of verifying the Contractor's invoices and the Contractor shall fully co-operate with any examination.

6.6	If the Client fails to make a payment that is properly due within 5 days of the date fixed for payment the Contractor will be entitled to claim interest on the overdue amount at 4 per cent per annum above the Bank of England Base Rate from the due date until the date of payment.

7.	CHANGE & DELAY

Change

7.1	The Client has the right to request changes and these may include additions to or deductions from the scope of the Works.  These requests shall be confirmed in writing and, within three (3) working days of receipt, the Contractor shall inform the Client in writing whether the proposed change will have an affect on the Contract Price and/or the time for completing the Works and, if so, the estimated amount of the extra or reduced cost and the likely change in the Completion Date.

7.2      The Contract Price may change if the market price of materials will increase by 10% compared to their cost at the day when the Contract was signed.

7.3	Once a change and its impact on the Contract Price and Completion Date are agreed, the Contractor shall prepare an appropriate Change Confirmation specifying the adjustment in the Contract Price and/or the Completion Date and give this to the Client.  No change shall be carried out unless it is confirmed by a Change Confirmation signed by the Client.

7.4	If no agreement is reached, the Client may withdraw the change request.  Alternatively, the Client can instruct the Contractor to proceed with the change before agreement is reached.  In that case the change shall be performed at the appropriate rates specified in the Contract or, in the absence of pre-agreed rates, at the Contractor's net costs plus ten (10) per cent.

7.5	If the Contractor believes that any act or omission of the Client constitutes a change, the Contractor must, within three (3) working days of the relevant event, submit a written request for a variation stating the basis for the request, the cost and the effect on the programme and Completion (if any) and the procedure in this clause 7 shall then be followed.

Delay

7.6     The contract may not be completed in time due to results from events or circumstances outside Contractor’s reasonable control, including but not limited to acts of God, strikes, lock outs, accidents, war, fire, breakdown of plant or machinery or shortage or unavailability of raw materials from a natural source of supply.

7.7	The Contractor must notify the Client within three (3) working days of becoming aware of any event beyond the Contractor’s control which may prevent or delay completion of the Works by the Completion Date.   The notice must specify the cause of the delay, the likely effect on the Completion Date and the Contractor's proposals for dealing with the matter.   The notice should be accompanied by relevant supporting documents and calculations.

7.8	The Contractor shall be given an extension of time if the Client is satisfied that completion of the Works is delayed for reasons beyond the Contractor's control and that the Contractor has used their best endeavours to mitigate or avoid the delay.  The Client or their representative, when giving notice of an extension of time, will specify the revised Completion Date.

7.9	An extension of time and extra expenses will be given for:

- Unforeseen ground conditions unless they could not have been foreseen by a contractor before commencing the works, who had seen all available information and reports and inspected the site before signing the Contract;

- Any other cause which couldn’t have been foreseen and avoided by the Contractor.

7.10	If an extension of time is given, it does not follow that extra money will be due even if the Contractor does incur extra costs and none will be allowed for: any delay in obtaining materials or equipment that are the responsibility of the Contractor; adverse weather (unless this is exceptionally severe so as to prevent work on site for more than two consecutive days); delay in getting any consent from a local authority, utility company or any other official organisation unless the Contractor can show the delay is abnormal and not in any way the fault of the Contractor; or due to any other cause that could have been foreseen and avoided by Contractor.

8.	ACCEPTABILITY OF WORKS

If during the course of the Works any materials or workmanship are not, in the opinion of the Client or their representative, in conformity with the Contract, or if the rate of progress is too slow, the Contractor shall, at no cost to the Client, rectify the problem, replace materials, re-perform work, or expedite progress, as directed by the Client or their representative. All works and quality should be in line with current building regulations and British standards.

9.	COMPLETION, DEFECTS & LIQUIDATED DAMAGES.

Completion

9.1	The Contractor shall give the Client notice when the Contractor considers the Works have been completed, all tests have been completed satisfactorily and the Works are ready for handover to the Client.  After the Works have been inspected by the Client and the Client’s representative (if any) and found to be complete, the Client (or the Client’ representative) shall issue a completion certificate to the Contractor specifying the Completion Date.

9.2	Where equipment or materials have the benefit of a manufacturer’s warranty, the Contractor shall ensure that the Client has the benefit of that warranty on completion (but this will not relieve the Contractor of their obligations under the Contract).

Defects

9.3	The Contractor shall be liable for any defects in the Works that occur during the Defects Period.  The Client shall promptly notify the Contractor of any defect in the Works that appears, and the Contractor shall be responsible for remedying the defect.  If the Contractor fails to take remedial action within a reasonable time, the Client may arrange for the work to be carried out by another contractor, in which case the Contractor shall be responsible for all costs properly incurred by the Client.

9.4	The Defects Period in respect of remedial work carried out by the Contractor shall recommence on the date that the remedial work is accepted by the Client as completed.

9.5	If the Contractor fails to complete the Works by the Completion Date, the Contractor shall be liable to pay the Client liquidated damages at the rate of £350/week of delay.  These may be deducted by the Client from any amount owing to the Contractor.

10.	INSURANCE & INDEMNITY

10.1	The Contractor and the Client shall each maintain the insurance policies suitable for their trade.

10.2	All insurances shall be taken out with reputable insurers without any unusual terms and each party shall provide the other with an insurance certificate on request.

10.3	The Contractor shall indemnify the Client against all liabilities, losses and claims, including costs, arising out of the death, injury or illness of any person and/or loss of or damage to the property of the Client or of any third party to the extent that the same is attributable to any act, negligence or default of the Contractor.  This indemnity also covers any third-party claim for infringement of intellectual property rights.

11.	OWNERSHIP & RISK

11.1	Ownership of equipment and materials to be provided by the Contractor for incorporation in the work shall pass to the Client upon delivery to Site or when wholly or partly paid for by the Client, if earlier.  The Contractor shall then mark them as Client property.  Risk of loss or damage to equipment and materials remains with the Contractor until Completion.

12.	TERMINATION & SUSPENSION

Termination

12.1	The Client may give notice to terminate the Contract if the Contractor commits a breach of contract or fails to comply with the Client’s reasonable directions.

12.2	The Contractor may give notice to terminate the Contract if the Client fails to make any payment properly due to the Contractor within 7 days of the payment date or commits any other material breach of the Contract.

12.3	Either party may give notice to terminate the Contract if the other party is unable to pay their debts, becomes insolvent or has a receiver, manager or administrative receiver or liquidator appointed or if there are good reasons for expecting that one of these events will occur.

12.4	 The Client may employ another contractor to complete the work.  The Contractor shall be entitled to be paid for work properly performed in accordance with the Contract but shall be liable to the Client for all extra costs and expenses incurred by the Client in having the Works completed by another contractor.  No money shall be payable to the Contractor following termination until the Client's recoverable costs and expenses have been assessed and paid to the Client by the Contractor or deducted from money owing to the Contractor.

12.5	The Client shall be entitled to give 14 day notice to terminate the Contract with respect to all or part of the Works at any time by giving notice to the Contractor.  In the event of partial termination, the Contract Price shall be equitably adjusted by agreement.

12.6	If the Client terminates for their own convenience under clause 12.5, compensation to the Contractor shall comprise payment for all Works completed in accordance with the Contract at the termination date plus the Contractor’s reasonable and unavoidable costs incurred because of the early termination.

Suspension

12.7	The Client may give 7 day notice to the Contractor to suspend all or part of the Works and, in that case, the Contractor shall make the Site safe and stop work.  The Client shall pay for Works carried out up to the date of suspension and shall reimburse the Contractor’s reasonable and unavoidable costs incurred in complying with the suspension notice and in remobilising when notice to resume work is given by the Client.  If suspension continues for more than 3 months, either party can give notice to terminate the Contract.

13.	CLIENT SUPPLIED MATERIALS & EQUIPMENT GUARANTEES

When the Client issues materials to the Contractor free of charge, those materials shall remain the property of the Client and must be maintained by the Contractor in good condition.  They shall be used solely in connection with the Contract and any materials surplus to requirements shall be returned to the Client or disposed of at the Client's direction.  Materials lost or damaged while in the custody of the Contractor shall be replaced or made good at the Contractor's expense. Also, any contractor materials supplied under this agreement are surplus must be left on site for use on future projects, unless a written agreement is made for the Contractor to take them.

14.	THIRD PARTY RIGHTS

14.1	A purchaser of property in the Project will have the right to enforce these Terms & Conditions by virtue of the Contracts (Rights of Third Parties) Act 1999.

14.2	If required by a lender that provides finance for the Project the Contractor shall enter into a deed of collateral warranty in favour of that lender within 14 days of being requested by the Client.

15.	GENERAL

15.1	Notices.  Every notice required under the Contract must be in writing and delivered by hand or sent by first class post to the address of the recipient.  A notice sent by post shall be treated as having been received two working days after posting.  A notice delivered by hand shall be treated as having been received at the time of delivery unless this is after the normal working hours of the recipient, in which case delivery shall be treated as occurring at 9.00 a.m. on the next working day.

15.2	Assignment.  Neither party shall assign any of their rights or obligations under the Contract without the prior written consent of the other.

15.3	Subcontracting.  The Contractor shall not sublet all of the Works, but shall be entitled to sublet parts of the Works after obtaining the Client’s consent, which shall not be unreasonably withheld.  Subcontracting shall not relieve the Contractor of its obligations under the Contract.

15.4	Entire Agreement.  The Contract is the only agreement between the parties relating to the Works and supersedes any previous arrangements, agreements or understandings relating to the Works.

15.5	Amendment.  Any amendment to the terms of the Contract shall only be effective if in writing and signed by the Client and the Contractor.

15.6	Severance.  If any provision of the Contract becomes illegal or unenforceable, this shall not affect the legality or enforceability of any other provision of the Contract.  In that situation the parties shall, where possible, use reasonable endeavours to agree an alternative provision which is legally enforceable.

15.7	Waiver.  The failure by a party to enforce any provision of the Contract shall not be treated as a waiver of that provision, nor shall it affect the right of that party subsequently to enforce that provision.

16.	SETTLEMENT OF DISPUTES & LAW

16.1	The parties will endeavour to settle any dispute or difference amicably by direct negotiation.

16.2	If they are unable to settle the dispute, it may be referred by either party to adjudication in accordance with the CEDR (Centre for Effective Dispute Resolution) Adjudication Rules unless another procedure is named in the Appendix.  The decision of the adjudicator shall be final and binding on the parties unless a notice of dissatisfaction is served by either party to the other within 28 days of the decision.

16.3	If a dispute under the Contract is related to a dispute between the Client and another contractor or consultant of the Client, then the Client may require that the same adjudicator deals with both disputes.

16.4	The parties may agree to refer a dispute to mediation in which case any other procedure under this clause 16 shall be delayed until 42 days after the mediator has been appointed (or other period agreed by the parties).  The mediation shall be conducted in accordance with the procedure named in the Appendix

16.5	Any dispute that is not resolved by negotiation or adjudication shall be finally settled by the courts of England and Wales.

16.6	The Contract is governed by the laws of England and Wales.

17.	DEFINITIONS

In these Terms & Conditions:

| “Appendix” | means the Appendix attached to the Form of Agreement; |
| --- | --- |
| “CDM Regulations” | means the Construction Design & Management Regulations 2015 (including any amendments); |
| "Completion Date" | means the date specified in the Appendix being the date upon which the Works are to be completed (as amended under the Contract); |
| "Contract" | means the Form of Agreement together with the Appendix and Schedules attached (and including documents listed in the Schedules as being part of the Contract); |
| "Contract Price" | means the amount payable for the Works as detailed in Schedule 1 (as amended under the Contract); |
| "Contractor" | means the contractor named in the Form of Agreement; |
| “Defects Period” | means the period specified in the Appendix during which the Contractor is responsible for remedying defects that appear in the Works; |
| "Effective Date" | means the date upon which the Works are to be commenced as stated in the Appendix; |
| “Form of Agreement” | means the form of agreement signed by the Client and the Contractor; |
| “Project” | means the Client’s project which includes the Works; |
| "Schedules" | means the attached numbered Schedules; |
| “Site” | means the place where the Project is to be carried out; |
| “Specification” | means the detailed specification for the Works; and |
| "Works" | Means the construction works and services, including design, to be provided by the Contractor which are expressed in, necessary and/or to be implied from the Contract. |

APPENDIX

| Contract Price | £ #total amount including profit and vat# |
| --- | --- |
| Effective Date | #todays date# |
| Access Date on site | #project start date# |
| Completion Date | #project end date# |
| Working hours | 9.00 am to 5.00 pm Monday to Friday & 9.00 am to 1 pm on Saturday Other times by prior agreement |
| Defects Period | #defects period# months from completion. |
| Planning Consents Party Wall Consents Building Regulations Utility Company (water) | Responsible party: #planning consents# #party wall consents# #building regulations# #utility water# |
| Site facilities to be provided by Client | Water, Electricity, Gas, Toilet Skips/waste arrangements to be handled by Contractor |
| Principal Designer | #principal designer# |
| Principal Contractor | #principal contractor# |
| Liquidated Damages | £150 for each week of delay after the final payment was made |
| Client’s Representative: | N/A |
| Architectural drawings | N/A |
| Adjudication Procedure: | Not defined |
| Mediation Procedure: | Not defined |

SCHEDULE 1

Description of Works

& Pricing

Location of Site:

# #project address# Job description: #job description#

SCHEDULE 2

Contract Price & Terms of Payment

Contract Price

The Contract Price is £ #total amount including profit and vat#

This is made up of the items priced in Schedule 1.

Payment Schedule

The Client shall make payments to the Contractor for the Works which have been carried out by the Contractor as follows.

- The Client will provide the contractor with an initial #deposit percent# % deposit upfront to cover materials

- £ #deposit#) Before work starts.

- The client must pay the leftover of the agreed sum no later than 10 working days from the date of satisfactory completion of snagging.

- Any additional work will be charged for. Customer will be notified if any additional work is needed. Additional work won’t be done prior to customer’s agreement.

- Money will then be released as stage payments. Contractor will submit invoice along with video of refurbishment progress and with following email stating what was the progress since last payment.

- The payment process is as follows 1) Invoices are submitted, 2) Work is checked by Client, 3) Payment is made no later than 10 working days since invoice submitted.

#list of works with client prices#